## Project Timeline
CU-Connect (1yr Forward)
PROJECT TITLE |  | CU-Connect |  | COMPANY NAME |  |  | Cairn University
PROJECT MANAGER |  | Miguel Tapia |  | DATE |  |  | 2020-05-06
# | Milestone |  | DETAILS | Q3 | [5 empty] | Q4 | [5 empty] | Q1 (2021) |  |  |  | Q2 (2021)
|  |  |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB | MAR | APR |  | MAY |  |  | JUN
1 | Port Application to React (Release-Q3 End) |  | - Provides SPA experience | Plan / Design
|  |  | - Ease of transition to React Native |  | Build (75% Front End)
|  |  | - Cleaner code and modularity |  |  |  |  | Test
Dep.
2 | Mobile Application - React Native (Release-2021 Q1 End) |  | - Accounts for alumni on mobile | [6 empty] | Plan (Native Imp.)
|  |  | - Ease of use | [7 empty] | Design
|  |  | - Quickly access news and event calander | [9 empty] | Front-End Native Arc.
|  |  | - Messaging system readily avaliable | [11 empty] | Back-End Architecture
|  |  | - Cross platform (iOS & Android) | [13 empty] | Test (Scalability)
|  |  | - Native feel | [15 empty] | Dep.
3 | Custom Proprietary Donation (Release-2021 Q2 1/2) |  | - No need for another separate entity | [16 empty] | Plan / Design
|  |  | - Allows data capture and metrics | [17 empty] | Build
|  |  | - Greater flexibiltiy and control | [18 empty] | Test
|  |  | - Custom campaings | [19 empty] | Dep
4 | Alumni Report Module (Release-2021 Q2 End) |  | - Featured donation options (campaigns) | [20 empty] | Plan / De
|  |  | - Custom reports and metrics | [21 empty] | Build
|  |  | - Quick access to transcripts | [22 empty] | Test
|  |  | - Access to donation reports for taxes | [23 empty] | Dep