## SUM
Student Name: | Miguel Tapia
Date | 2020-05-05 |  | Plan vs. Actual Analysis
Project Name | CU-Connect
| Project Phase | Plan | Actual | Difference
| Planning | 12 | 12 | 0
| Design | 10 | 9 | 1
| Coding | 75 | 70 | 5
| SIT | 7 | 4 | 3
| UAT | 6 | 3 | 3
| Training / Documentation | 9 | 5 | 4
| Deployment | 1 | 3 | -2
| Hypercare | 9 | 5.5 | 3.5
| Risk | 8 | 8 | 0
|  | 137 | 119.5 | 17.5
Period 1 - 1st through 15th
Period 2 - 16th through month-end

## 2-11
Time Reporting Week Ending | 2020-02-12 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total Hours
0
| Planning | [7 empty] | 0
| Design | 1 |  |  |  | 1 | 1.5 |  | 3.5
| Coding | [7 empty] | 0
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
3.5

## 2-19
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-02-19 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design |  |  |  |  | 1.5 | 1.5 | 2.5 | 5.5
| Coding | [7 empty] | 0
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
5.5

## 2-23
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-02-23 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  |  |  | 1.5 | 1.5 | 2 | 6 | 11
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
11

## 3-01
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-03-01 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  |  | 2 | 4 | 1 | 1 |  | 8
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
8

## 3-15
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-03-15 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  | 3 | 2 | 3 | 1 | 1 |  | 10
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
10

## 3-22
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-03-22 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  | 5 | 5 | 5 | 5 | 5 |  | 25
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
25

## 3-29
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-03-29 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  | 3 | 2 | 2 | 2 | 3 |  | 12
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
12

## 4-05
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-04-05 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  |  |  |  | 1 |  |  | 1
| SIT | [5 empty] | 2 |  | 2
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare | [7 empty] | 0
0
0
3

## 4-12
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-04-12 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding | [7 empty] | 0
| SIT |  |  |  | 1 | 1 |  |  | 2
| UAT | [5 empty] | 1 |  | 1
| Training / Documentation | [7 empty] | 0
| Deployment | [5 empty] | 2 |  | 2
| Hypercare | [7 empty] | 0
0
0
5

## 4-19
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-04-19 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding | [7 empty] | 0
| SIT | [7 empty] | 0
| UAT |  |  |  |  | 1 | 1 |  | 2
| Training / Documentation |  |  | 2 |  | 2 | 1 |  | 5
| Deployment | [5 empty] | 1 |  | 1
| Hypercare | [7 empty] | 0
0
0
8

## 4-26
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-04-26 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding |  |  |  | 1 | 1 | 1 |  | 3
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare |  | 1 | 1 |  |  |  |  | 2
0
0
5

## 5-03
Student Name: | Miguel Tapia
Time Reporting Week Ending | 2020-05-03 |  |  |  | Weekly Time Reporting Sheet
Project Name | CU - Connect
| Project Phase | SUN | MON | TUE | WED | THU | FRI | SAT | Total Hours
0
| Planning | [7 empty] | 0
| Design | [7 empty] | 0
| Coding | [7 empty] | 0
| SIT | [7 empty] | 0
| UAT | [7 empty] | 0
| Training / Documentation | [7 empty] | 0
| Deployment | [7 empty] | 0
| Hypercare |  |  | 0.5 | 1 | 1 | 1 |  | 3.5
0
0
3.5