## Gantt Chart
Alumni Portal GANTT Chart
PROJECT TITLE |  | Cairn University's Alumni Portal Overhaul | [19 empty] | COMPANY NAME | [6 empty] | Cairn University
PROJECT MANAGER |  | Miguel Augusto Tapia | [19 empty] | DATE | [6 empty] | 2020-02-05
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ZERO | [14 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | 2020-01-22 |  |  |  |  | 2020-01-29 |  |  |  |  | 2020-02-05 |  |  |  |  | 2020-02-12 |  |  |  |  | 2020-02-19 |  |  |  |  | 2020-02-26 |  |  |  |  | 2020-03-04 |  |  |  |  | 2020-03-11 |  |  |  |  | 2020-03-18 |  |  |  |  | 2020-03-25 |  |  |  |  | 2020-04-01 |  |  |  |  | 2020-04-08 |  |  |  |  | 2020-04-15 |  |  |  |  | 2020-04-22 |  |  |  |  | 2020-04-29
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Planning | 12
1.1 | Project Overview | 2020-01-22 | 2020-01-22 | 3 | 100% | bar: 2020-01-22 W
1.2 | Research | 2020-01-23 | 2020-01-29 | 3 | 100% | bar: 2020-01-22 R to 2020-01-29 W
1.3 | Formal Proposal | 2020-01-30 | 2020-02-05 | 2 | 100% | bar: 2020-01-29 R to 2020-02-05 W
1.4 | Document Signatures | 2020-02-05 | 2020-02-07 | 1 | 100% | bar: 2020-02-05 W to 2020-02-05 F
1.5 | Team Gathering | 2020-02-05 | 2020-02-07 | 1 | 100% | bar: 2020-02-05 W to 2020-02-05 F
1.6 | Guidelines | 2020-01-22 | 2020-02-07 | 1 | 100% | bar: 2020-01-22 W to 2020-02-05 F
1.7 | Project Initiation | 2020-02-05 | 2020-02-07 | 1 | 100% | bar: 2020-02-05 W to 2020-02-05 F
2 | Design | 10
2.1 | Gather design ideas | 2020-02-10 | 2020-02-11 | 2 | 100% | bar: 2020-02-12 M to 2020-02-12 T
2.2 | Wireframes | 2020-02-12 | 2020-02-12 | 2 | 100% | bar: 2020-02-12 W
2.3 | Gather color palette | 2020-02-13 | 2020-02-13 | 3 | 100% | bar: 2020-02-12 R
2.4 | Design document progression | 2020-02-10 | 2020-02-14 | 3 | 100% | bar: 2020-02-12 M to 2020-02-12 F
3 | Build: Front-End | 35
3 | Login Page | 2020-02-17 | 2020-02-20 | 2 | 100% | bar: 2020-02-19 M to 2020-02-19 R
3.1 | Update Information Page | 2020-02-21 | 2020-02-26 | 3.5 | 100% | bar: 2020-02-19 F to 2020-02-26 W
3.2 | Events Page | 2020-02-27 | 2020-03-03 | 3.5 | 0% | bar: 2020-02-26 R to 2020-03-04 T
3.3 | Reports Page * | 2020-03-04 | 2020-03-10 | 5 | 0% | bar: 2020-03-04 W to 2020-03-11 T
3.4 | Donate Page * | 2020-03-11 | 2020-03-17 | 5 | 0% | bar: 2020-03-11 W to 2020-03-18 T
3.5 | Admin Search Page | 2020-03-18 | 2020-03-20 | 2 | 0% | bar: 2020-03-18 W to 2020-03-18 F
3.6 | Admin Approval Page | 2020-03-21 | 2020-03-27 | 2 | 0% | bar: 2020-03-25 M to 2020-03-25 F
3.7 | Alumni Connect Page (Each Other) | 2020-03-28 | 2020-04-03 | 5 | 0%
3.8 | Student Connect Page (Alumni) | 2020-04-03 | 2020-04-09 | 5 | 0% | bar: 2020-04-01 F to 2020-04-08 R
3.9 | Admin Extra Mgmt. Page | 2020-04-10 | 2020-04-10 | 2 | 0% | bar: 2020-04-08 F
4 | Build: Back-End | 40
4 | Login Page (Back-End) | 2020-02-17 | 2020-02-20 | 1 | 100% | bar: 2020-02-19 M to 2020-02-19 R
4.1 | Update Information (Back-End) | 2020-02-21 | 2020-02-26 | 3.5 | 100% | bar: 2020-02-19 F to 2020-02-26 W
4.2 | Events Page (Back-End) | 2020-02-27 | 2020-03-03 | 3.5 | 0% | bar: 2020-02-26 R to 2020-03-04 T
4.3 | Reports Page (Back-End) * | 2020-03-04 | 2020-03-10 | 6 | 0% | bar: 2020-03-04 W to 2020-03-11 T
4.4 | Donate Page (Back-End) * | 2020-03-11 | 2020-03-17 | 6 | 0% | bar: 2020-03-11 W to 2020-03-18 T
4.5 | Admin Search Page (Back-End) | 2020-03-18 | 2020-03-20 | 3 | 0% | bar: 2020-03-18 W to 2020-03-18 F
4.6 | Admin Approval Page (Back-End) | 2020-03-21 | 2020-03-27 | 3 | 0% | bar: 2020-03-25 M to 2020-04-01 M
4.7 | Alumni Connect Page (Back-End) | 2020-03-27 | 2020-04-06 | 6 | 0% | bar: 2020-04-01 M to 2020-04-08 M
4.8 | Student Connect Page (Back-End) | 2020-04-03 | 2020-04-10 | 6 | 0% | bar: 2020-04-01 F to 2020-04-08 F
4.9 | Admin Extra Mgmt. Page (Back-End) | 2020-04-10 | 2020-04-10 | 2 | 0% | bar: 2020-04-08 F
5 | Testing | 13
5.1 | Systems Integration Testing (SIT) | 2020-04-13 | 2020-04-14 | 3 | 0% | bar: 2020-04-15 M to 2020-04-15 T
5.2 | User Acceptance Testing (UAT) | 2020-04-15 | 2020-04-16 | 3 | 0% | bar: 2020-04-15 W to 2020-04-15 R
5.3 | Unit Testing | 2020-04-16 | 2020-04-16 | 3 | 0% | bar: 2020-04-15 R
5.4 | Security / Reliability Testing | 2020-04-17 | 2020-04-20 | 3 | 0% | bar: 2020-04-15 F to 2020-04-22 M
5.5 | Scalability Testing | 2020-04-17 | 2020-04-17 | 1 | 0% | bar: 2020-04-15 F
6 | Training and Documentation | 9
6.1 | Training Preparation | 2020-04-20 | 2020-04-21 | 4 | 0% | bar: 2020-04-22 M to 2020-04-22 T
6.2 | Training Presentaiton | 2020-04-22 | 2020-04-22 | 0.5 | 0% | bar: 2020-04-22 W
6.3 | Documentation Preparation | 2020-04-20 | 2020-04-21 | 4 | 0% | bar: 2020-04-22 M to 2020-04-22 T
6.4 | Documentation Presentation | 2020-04-22 | 2020-04-22 | 0.5 | 0% | bar: 2020-04-22 W
7 | Deploy | 1
7.1 | Create Cloud User | 2020-04-23 | 2020-04-23 | 0.25 | 0% | bar: 2020-04-22 R
7.2 | Deploy Application | 2020-04-24 | 2020-04-24 | 0.75 | 0% | bar: 2020-04-22 F
8 | HyperCare | 9
8.1 | Total Avaliability | 2020-04-27 | 2020-05-01 | 4 | 0% | bar: 2020-04-29 M to 2020-04-29 F
8.2 | Bug Addressing | 2020-04-30 | 2020-05-01 | 4 | 0% | bar: 2020-04-29 R to 2020-04-29 F
8.3 | Optimizations | 2020-05-01 | 2020-05-01 | 0.5 | 0% | bar: 2020-04-29 F
8.4 | HyperCare Closure | 2020-05-01 | 2020-05-01 | 0.5 | 0% | bar: 2020-04-29 F
9 | Risk | 20
9.1 | Project Objectives | 2019-03-23 | 2020-05-01 | 20 | 0% | bar: 2020-03-25 M to 2020-04-29 F
|  | TOTAL HOURS: |  | 137
|  | TOTAL COST: |  | 13700